## Timeline
TIMELINE TEMPLATES by Vertex42.com
https://www.vertex42.com/ExcelTemplates/timeline.html
Tips for Using this Template
• Insert and delete entire rows when editing the data tables
• Avoid leaving the label column blank
• Format the horizontal axis to set min/max bounds
• Enter a vertical position between -100 and 50
• Format individual data labels or markers to highlight specific events
Other Notes
• Milestone leader lines are Y Error bars
• Task leader lines are Y Error bars
• Task durations are X Error bars
Tasks
Start | End | Duration | Label | Vert. Position | Vert. Line
2023-04-10 | 2023-04-16 | 7 | Week 1: Research and Conceptualization Apr 10 - Apr 16 | -25 | -25
2023-04-17 | 2023-04-23 | 7 | Week 2: Project Setup Apr 17 - Apr 23 | -45 | -20
2023-04-24 | 2023-04-30 | 7 | Week 3: Game Design and Mechanics Apr 24 - Apr 30 | -70 | -25
2023-05-01 | 2023-05-07 | 7 | Week 4: UI and UX Development May 1 - May 7 | -90 | -20
2023-05-08 | 2023-05-14 | 7 | Week 5: Audio Integration May 8 - May 14 | -35 | -35
2023-05-15 | 2023-05-21 | 7 | Week 6: Database and Backend Design May 15 - May 21 | -55 | -20
2023-05-22 | 2023-05-28 | 7 | Week 7: Backend Integration May 8 - May 14 | -20 | -20
2023-05-29 | 2023-06-04 | 7 | Week 8: Asset Creation and Integration May 8 - May 14 | -70 | -50
2023-06-05 | 2023-06-11 | 7 | Week 9: Testing and Debugging May 8 - May 14 | -90 | -20
2023-06-12 | 2023-06-18 | 7 | Week 10: Additional Features and Polish May 8 - May 14 | -35 | -35
2023-06-19 | 2023-06-25 | 7 | Week 11: Final Testing and Deployment May 8 - May 14 | -55 | -20
2023-06-26 | 2023-07-02 | 7 | Week 12: Documentation and Portfolio May 8 - May 14 | -75 | -20
Insert new rows above this one
Milestones
Date |  |  | Label | Position
2023-04-10 |  |  | Start, Apr 10 | 30
2023-05-07 |  |  | Milestone #1 | 25
2023-06-04 |  |  | Milestone #2 | 20
2023-07-02 |  |  | Deliver, Jul 2 | 30
Insert new rows above this one
Additional Information
Weeks
Week 1: Research and Conceptualization Research existing rhythm games to understand mechanics and features. Define the game's concept, gameplay, and target audience. Sketch out the game's user interface and user experience.
Week 2: Project Setup Set up a GitHub repository to host the project. Install and configure Unity, .NET Visual Studio, and MySQL Workbench. Set up Unity WebGL build target for web deployment. Create a basic Unity project structure and scene layout.
Week 3: Game Design and Mechanics Design the game mechanics, such as note timings, scoring, and difficulty levels. Implement a basic note spawning and timing system in Unity. Develop the input handling system for detecting player input and calculating scores.
Week 4: UI and UX Development Design and create game menus, including start, options, and pause screens. Implement a user interface for the gameplay scene, such as score display and combo counters. Develop a system for handling different screen resolutions and aspect ratios.
Week 5: Audio Integration Implement an audio system to load and play music tracks. Synchronize the note spawning with the audio playback. Add audio effects for successful and missed notes.
Week 6: Database and Backend Design Design the database schema for storing user data, scores, and other game-related information. Set up the MySQL database and connect it to your .NET Visual Studio project. Develop APIs for user registration, login, and score submission.
Week 7: Backend Integration Integrate the .NET backend with the Unity frontend using a REST API or UnityWebRequest. Implement user registration and login functionality in Unity. Implement score submission and leaderboard display.
Week 8: Asset Creation and Integration Create or source game assets, such as sprites, animations, and background images. Integrate the assets into the Unity project. Optimize assets for performance and load times.
Week 9: Testing and Debugging Test the game mechanics, UI, and backend integration. Identify and fix bugs and issues. Optimize the game for performance and stability.
Week 10: Additional Features and Polish Implement additional features, such as achievements and unlockables. Add visual and audio polish to enhance the game experience. Implement user settings, such as audio and input customization.
Week 11: Final Testing and Deployment Perform thorough testing of the game, including stress tests on the backend. Resolve any remaining issues and apply final optimizations. Deploy the game to GitHub Pages and set up the domain.
Week 12: Documentation and Portfolio Document your development process, including challenges and solutions. Create a project summary, showcasing the game's features and mechanics. Update your portfolio with the rhythm game project, including a link to the GitHub repository and a playable demo.
Formulas:
End = [Start]+[Duration]-1
Start = [End, row above]+1

## About
PROJECT TIMELINE by Vertex42.com
https://www.vertex42.com/ExcelTemplates/project-timeline.html
About This Template
This template uses a scatter chart with data labels and error bars to create a project timeline that shows both milestones and tasks with durations. Unlike a Gantt chart, which shows each task on a separate row, you control the vertical positioning of tasks within the timeline. You can specify the length of the vertical leader line to help show task dependencies.
This type of project timeline is mainly useful for a general overview of a project rather than showing a detailed work breakdown structure.
More Templates
Visit Vertex42.com to download other timeline and project management templates.
More Timeline Templates
More Project Management Templates
About Vertex42
Vertex42.com provides professionally designed spreadsheet templates for business, home, and education - most of which are free to download. Their collection includes a variety of calendars, planners, and schedules as well as personal finance spreadsheets for budgeting, debt reduction, and loan amortization.
Businesses will find invoices, time sheets, inventory trackers, financial statements, and project planning templates. Teachers and students will find resources such as class schedules, grade books, and attendance sheets. Organize your family life with meal planners, checklists, and exercise logs. Each template is thoroughly researched, refined, and improved over time through feedback from thousands of users.